## Slide 1: Part 7 - II: Project Cost Management
7.3 Control Costs by EVM Calculations

## Slide 2: Control Costs (Earned Value Management)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
How to stay in budget...

## Slide 3: Control Costs – PV (Planned Value)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
Hours worked (till now)
Total duration (of project)

## Slide 4: Control Costs – PV (Planned Value)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”

## Slide 5: Control Costs – EV (Earned Value)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”

## Slide 6: Control Costs – EV (Earned Value)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
Earned Value vs Actual Cost?
EV, measures the work that has been done (in $) by looking at the schedule...
AC, tells how much you have spent so far... (You may need extra equipments, extra workers, you may be effected by currency changes etc.)

## Slide 7: Control Costs – MS Prj.  PV & EV
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
How to show completed percentage at MS Project...

## Slide 8: Control Costs – SPI & SV
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”

## Slide 9: Control Costs – CPI, CV, TCPI
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
What schedule says vs what happened in real...

## Slide 10: Control Costs – Summary
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”

## Slide 11: Control Costs – EAC (Estimate at completion)
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
20.000 0.8
= 25.000
20.000 1.1
= 18.181
Planned End Date SPI
EAC (schedule) =

## Slide 12: Control Costs – ETC & VAC
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”
Remaining amount ($) that has to be spend to complete the project...

## Slide 13: Control costs...
  Outputs:
    Work Performance Measurements: Calculated CV, SV, CPI and SPI values for WBS components, in particular the work packages and control accounts, are documented and communicated to stakeholders.
    Budget Forecasts: Either a calculated EAC value or a bottom-up EAC value is documented and communicated to stakeholders.
    OPA Updates
    Change Requests
    Project Management Plan Updates
      Cost Performance Baseline
      Cost Management Plan
    Project Document Updates
      Cost Estimates
      Basis of Estimates
Process of “monitoring the status of the project to update the project budget and managing changes to the cost baseline.”

## Slide 14
- Part 7: Control Costs / EVM Case Study -
By focusing on the outputs of first day and by applying EVM formulas (if necessary), decide on:
  the duration of the project,
  if we are above or below the project’s budget & schedule,
  howmuch we are above or below the budget & schedule,
  the estimated budget, cost overrun + schedule over run amounts (if exists) at completion, * Assume we are not modifying the performance of the project!
  what to do, if we want to stay in budget (TCPI for cost & schedule).

## Slide 15: Solution
Planned Value

## Slide 16: Solution

## Slide 17: Solution

## Slide 18: Solution
0,58

## Slide 19: Solution

## Slide 20: Solution

## Slide 21: Solution
Planned Value

## Slide 22: Solution

## Slide 23: Solution
EAC = BAC / CPI
1740 / 0,58 = 3000

## Slide 24: Solution
?
?

## Slide 25: Solution
-1260$
6 Planned End Date 0,7 SPI
= 8.57 days

## Slide 26: Summary :
8.57 * 350 (AC) =
6  70
?  100
TCPI for budget: 1.10
TCPI for schedule: 1.06
A TCPI value greater than 1 indicates a need for increased performance for the remaining work of the project in order to stay within budget !